## Sheet1
|  |  |  | Jason Surgery |  | Mike Contract Up | Extra Features
| July 16-20 | July 23-27 | July 30 - Aug 3rd | Aug 6 -10 | Aug 13-17 | Aug 20-24 | custom creation of blob storage based on company name
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
TODO | Set up framework for web app | incorporate client feedback | Add KPMG Context | Bug Fix | Bug Fix | Bug Fix
| Set up framework for blob storage | Build form & wrapper | Exec Summary View | incorporate client feedback | incorporate client feedback | incorporate client feedback
| Create Power BI dummy dashboard | Create KPI Inventory, bucket by service and industry - ask for outside help | Analyst View Dashboards
| Connect Blob to power bi | Connect web app to blob storage | incorporate client feedback
embed dashboard in web app
Deliverable | Excel doc connected to power BI via blob, embedded in web app | working client flow - fill out questionaire, submit data, receive dashboard | Clean looking analyst and executive views, showing relevant insights for the client | Polished asset | polished asset | final product
Client Meeting | Show mock up of analyst view dashboard, get feedback | Have client go through questionaire and data submission flow | Have client review KPIs, provide feedback on visualization and KPIs used. | client reviews the polished asset, delivers feedback | client reviews the polished asset, delivers feedback | final product review
Extra Goals | Week 1: Designing form framework
Implementing for framework